## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | US1/N1 | Developer | Understand the problem | I can search for relevant solutions | 1
1 | US1/N2 | Developer | Understand user stories | I can search for dataset accordingly | 1
1 | SB1/US1 | Researcher | Learn about Big Data | I Can get the basic knowledge | 1
1 | SB1/US2 | Researcher | Data Collection | I Can get the basic knowledge | 1
1 | SB1/US3 | Researcher | Filtering of Data | I Can Analyse the data | 1
1 | SB1/US4 | Researcher | Pre-Installation Setup | I Can Analyse the data | 1
1 | SB1/US5 | Researcher | Hadoop Installation | I Can Analyse the data | 1
1 | SB1/US6 | Researcher | Verifying Data | I Can Analyse the data easily | 1
1 | SB1/US7 | Researcher | Start HDFS | I Can continue with the project | 1
1 | SB1/US8 | Researcher | Compilation and Execution of Process Units Program | I Can make all programs like word count etc | 1
2 | SB1/US9 | Researcher | LEARNING Other Tech. | I Can Analyse the data easily | 2
2 | SB1/US10 | Researcher | Do PIG Installation | I Can access PIG environment | 2
2 | SB1/US11 | Researcher | Do HIVE Installation | I Can access HIVE environment | 2
2 | SB1/US12 | Researcher | Do SPARK Installation | I Can access SPARK environment | 2
2 | SB1/US13 | Researcher | Download related Papers & project | I Can get to know all other related work done | 2
2 | SB1/US14 | Researcher | LEARNING ML | I Can implement in my project | 2
2 | SB1/US15 | Researcher | Learning about various algo. | I can implement them | 2
2 | SB1/US16 | Researcher | Implementation of naïve bayes(ML) | I can use it in my project | 2
2 | SB1/US17 | Researcher | Implementation of Decision Tree(ML) | I can use it in my project | 2
2 | SB1/US18 | Researcher | Implementation of Logistic Regrassion(ML) | I can use it in my project | 2
3 | SB1/US19 | Researcher | Implementation of naïve bayes(BD) | I can use it in my project | 3
3 | SB1/US20 | Researcher | Implementation of Decision Tree(BD) | I can use it in my project | 3
3 | SB1/US21 | Researcher | Implementation of Logistic Regrassion(BD) | I can use it in my project | 3
3 | SB1/US22 | Researcher | Accuracy Calculation(ML) | improve my performance | 3
3 | SB1/US23 | Researcher | Accuracy Calculation(BD) | I can work on it | 3
3 | SB1/US24 | Researcher | Comparative Analysis | I can Compare them | 3
3 | SB1/US25 | Researcher | present results | I can show them | 4

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - SPAM DETECTION
SB1/N1 | Understand the problem | SB1/D1/T1 | Breaking the problem and understanding each component | AB+VB+US
|  | SB1/D1/T2 | Searching for relavent solutions | AB+VB+US
|  | SB1/D1/T3 | Searching alternative approches | AB+VB+US
|  | SB1/D1/T4 | Analysing similar projects | AB+VB+US
SB1/N2 | Understand user stories | SB1/D2/T1 | Looking for various use cases | AB+VB+US
|  | SB1/D2/T2 | Discussion about user stories | AB+VB+US
|  | SB1/D2/T3 | Searching for type of data required | AB+VB+US
SB1/US1 | LEARNING BIG DATA | SB1/D1/T2 | Learning about Big Data Hadoop | AB+VB+US
|  | SB1/D1/T3 | Learning about Big Data HDFS | AB+VB+US
|  | SB1/D1/T4 | Learning about Big Data Mapreduce | AB+VB+US
|  | SB1/D1/T5 | Learning about Big Data Echosystem | AB+VB+US
SB1/US2 | DATA COLLECTION | SB1/D2/T1 | Downloading datasets from github | AB+VB+US
|  | SB1/D2/T2 | Downloading datasets from kaggle | AB+VB+US
|  | SB1/D2/T3 | Downloading datasets from popular dataset sites | AB+VB+US
SB1/US3 | FILTERING OF DATA | SB1/D3/T1 | Data cleaning | US
|  | SB1/D3/T2 | Applying Transformations | AB+US
|  | SB1/D3/T3 | Removing Null values | VB
|  | SB1/D3/T4 | Data screening | AB
SB1/US4 | Pre-installation Setup | SB1/D4/T1 | Linux platform | VB
|  | SB1/D4/T2 | Installing Java | US
|  | SB1/D4/T3 | setting up PATH | US
|  | SB1/D4/T4 | Download and extract Hadoop | VB
|  | SB1/D4/T5 | Setting Up Hadoop | AB
SB1/US5 | HADOOP INSTALLATION | SB1/D4/T1 | Installing single node cluster | AB
|  | SB1/D4/T2 | Installing SSH localhost | AB
|  | SB1/D4/T3 | Setting up the paths | VB
|  | SB1/D4/T4 | Disable the Ipv6 | US
|  | SB1/D4/T5 | changing Bashrc file | AB
SB1/US6 | Verifying Hadoop Installation | SB1/D6/T1 | Hadoop Configuration | AB
|  | SB1/D6/T2 | Verifying Hadoop dfs | AB
|  | SB1/D6/T3 | Verifying Yarn Script | AB
|  | SB1/D6/T4 | Accessing Hadoop on Browser | VB+US
SB1/US7 | HDFS | SB1/D7/T2 | Starting HDFS | VB+US
|  | SB1/D7/T3 | Listing Files in HDFS | VB+US
|  | SB1/D7/T4 | Inserting Data into HDFS | VB+US
|  | SB1/D7/T5 | Retrieving Data from HDFS | VB+US
SB1/US8 | Compilation and Execution of Process Units Program | SB1/D8/T1 | PROG-1(Word Count) | VB+US
|  | SB1/D8/T2 | PROG-2(Line Count) | VB+US
|  | SB1/D8/T3 | PROG-3(Case Study) | VB+US
|  | SB1/D8/T4 | PROG-4(Case Study) | VB+US

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 40 | 40 | Tasks
2018-09-11 | 15 | 40
2018-09-12 | 13 | 40
2018-09-14 | 6 | 40
2018-09-16 | 4 | 40
2018-09-18 | 2 | 40
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - SPAM DETECTION
SB1/US9 | LEARNING Other Tech. | SB2/D1/T1 | Learning about Pig | AB+VB+US
|  | SB2/D1/T2 | Learning about Hive | AB+VB+US
|  | SB2/D1/T3 | Learning about Hbase | AB+VB+US
|  | SB2/D1/T4 | Learning about various Algo | AB+VB+US
|  | SB2/D1/T5 | Learning about Basic Programs | AB+VB+US
SB1/US10 | PIG INSTALLATION | SB2/D1/T1 | Download Apache PIG | AB+VB+US
|  | SB2/D1/T2 | Installing PIG | AB+VB+US
|  | SB2/D1/T3 | Configured Apache PIG | AB+VB+US
|  | SB2/D1/T4 | Verifying Apache PIG | AB+VB+US
SB1/US11 | HIVE INSTALLATION | SB2/D2/T1 | Download Apache HIVE | AB+VB+US
|  | SB2/D2/T2 | Installing HIVE | AB+VB+US
|  | SB2/D2/T3 | Configured Apache HIVE | AB+VB+US
|  | SB2/D2/T4 | Verifying Apache HIVE | AB+VB+US
SB1/US12 | SPARK INSTALLATION | SB2/D3/T1 | Download Apache SPARK | AB+VB+US
|  | SB2/D3/T2 | Installing SPARK | AB+VB+US
|  | SB2/D3/T3 | Configured Apache SPARK | AB+VB+US
|  | SB2/D3/T4 | Verifying Apache SPARK | AB+VB+US
SB1/US13 | Download related Papers & project | SB2/D4/T1 | Designing of GUI | AB+VB+US
|  | SB2/D4/T2 | Finding modules required | AB+VB+US
|  | SB2/D4/T3 | Downloading and Installing the modules | AB+VB+US
SB1/US14 | LEARNING ML | SB2/D5/T1 | Studing naïve bayes model | AB+VB+US
|  | SB2/D5/T2 | Studing decision tree | AB+VB+US
|  | SB2/D5/T3 | Studing Logistic Regression model | AB+VB+US
SB1/US16 | Naive Bae Model ML | SB2/D6/T1 | Studying Naive Bayes Model | AB+VB+US
|  | SB2/D6/T2 | Implementing Naive Bayes Model | AB+VB+US
|  | SB2/D6/T3 | Implementing Naive Bayes Model on research data | AB+VB+US
SB1/US17 | Decision Tree ML | SB2/D7/T1 | Studying decision tree | AB+VB+US
|  | SB2/D7/T2 | Implementing decision tree | AB+VB+US
|  | SB2/D7/T3 | Implementing decision tree on research data | AB+VB+US
SB1/US18 | Logistic Regrassion ML | SB2/D8/T1 | Studying Logistic Regression | AB+VB+US
|  | SB2/D8/T2 | Implementing logistic regression | AB+VB+US
|  | SB2/D8/T3 | Implementing decision tree on research data | AB+VB+US

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 32 | 32 | Tasks
2017-09-28 | 15 | 32
2017-10-02 | 10 | 32
2017-10-05 | 4 | 32
2017-10-07 | 2 | 32
2017-10-09 | 1 | 32
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - SPAM DETECTION
SB1/US19 | Naive Bae Model BD |  | Studing naïve bayes model
Implementing naïve bayes model
Implementing naïve bayes model on Research data
SB1/US20 | Decision Tree BD |  | Studying decision tree
Implementing decision tree
Implementing decision tree on research data
SB1/US21 | Logistic Regrassion BD |  | Studying Logistic Regression
Implementing logistic regression
Implementing decision tree on research data
SB1/US22 | Accuracy Calculation(ML) |  | Calculating accuracy, recall & fvalue
searching for the other performance measures & calculating them
SB1/US23 | Accuracy Calculation(BD) |  | Calculating accuracy, recall & fvalue
searching for the other performance measures & calculating them
SB1/US24 | Comparative Analysis |  | Documentation about Big Data
Documentation about ML
Accuracy of the Big Data results
Accuracy of the Machine Learning results
Comparision between accuracy results of Big Data & ML
SB1/US25 | Present Results |  | Complete Documentation
Brief knowledge of ML
Brief knowledge of Big Data
Graphs & Charts
Research papers

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 37 | 37 | Tasks
2018-10-18 | 15 | 37
2018-10-20 | 14 | 37
2018-10-21 | 5 | 37
2018-10-22 | 2 | 37
2018-10-23 | 1 | 37
0
Days

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days